## Planning
Student | Tine Vancoillie
Datum | Taak | Tijd
2017-09-28 | Concept bedenken + logo + naam | 4
2017-10-03 | Ideeen, ideeenbord, moodboard, styletile | 2.25
2017-10-04 | Moodboard + styletiles afwerken, sitemap + wireframes | 4.5
2017-10-06 | Wireframes, wireflow, visual designs | 4.25
2017-10-07 | Visual designs | 4.5
2017-10-08 | Briefing, analyse, dossier, planning, mockups maken | 5
2017-10-09 | Analyse, planning (fases), style guide | 2.25
2017-01-13 | Install vue | 1
2017-10-20 | Install Drupal + post en get (Problemen) | 3.25
2017-10-23 | drupal: contenttype voertuig, laadpunten aanmaken en profiel gegevens toevoegen, rollen aanmaken + Vue: pagina’s aanmaken | 3.25
2017-10-25 | Module ‘efiara’ aanmaken + content entities: bookings, chargingpoints, owner, renter, owner charging points, vehicles aanmaken + velden toevoegen en nieuwe aanmaken | 4
2017-10-27 | problemen, opnieuw toevoegen velden + nieuwe aanmaken + rest toevoegen en testen postman | 3.75
2017-10-28 | Problemen port, rest, afbeelding field voertuigen toevoegen, get voertuigen in vue, problemen cors, design overview page, detail, get id proberen | 4.25
2017-10-29 | REST id, post, zelfstudie, vue detail design | 4.25
2017-10-30 | zelfstudie post + design + sidebar | 2.75
2017-10-31 | Sidebar, sass problemen, design | 3.5
2017-11-01 | Pagina's toevoegen (bookings, chargingpoints, info, login, my vehicles, profile, register) + login en register design + design | 4.25
2017-11-02 | Design, homepage, zelfstudie rest met relaties, aanpassen boeking in drupal, book-page in vue | 4.75
2017-11-03 | Sidebar design, google maps + geolocation | 4.75
2017-11-04 | Geolocation + entity's opnieuw aanmaken (fields toevoegen + add new) + rest + uitzoeken rest relationships | 5
2017-11-05 | pagina's in router + google maps + charging points | 5
2017-11-06 | Charging points + pagina profiel, create vehicles, aanvragen + get requests + design + calander | 5.25
2017-11-10 | Proberen inloggen + registreren, "IP address temporarily blocked", account velden aanpassen, relations | 3
2017-11-11 | Request in cache uitzoeken, options toevoegen, proberen login + post booking, post vehicles in postman | 4.5
2017-11-12 | proberen login + post booking | 1.5
2017-11-13 | Bookings problems | 4.75
2017-11-14 | Login/logout, sidebar, auth.js, register | 3.5
2017-11-17 | Booking, detail, problems, status request | 5
2017-11-18 | Request + bookings + vehicles from user, renter/owner veranderen door eigenaar, post book, logout proberen | 3.25
2017-11-19 | Voorwaarden, design | 2.5
2017-11-20 | const url, bookings, orderby, create vehicle, profile edit | 4.5
2017-11-21 | Uitzoeken patch | 2.5
2017-11-24 | Create booking, edit your vehicle | 4.25
2017-11-25 | Edit booking, create & edit in 1 component, problemen | 5.5
2017-11-26 | Create + edit vehicle in 1, patch vehicle proberen | 3.75
2017-11-28 | patch + authentication | 2.5
2017-12-01 | filteren, chargingpoints en status request | 4
2017-12-02 | status booking en request | 4.5
2017-12-03 | Status booking, validate (login, register, profile) | 3.75
2017-12-04 | css, auth in header | 2.5
2017-12-05 | auth in header, bereikbare dagen, zelfstudie veux | 3
2017-12-08 | disabled dates | 4
2017-12-09 | disabled dates | 3
2017-12-11 | filteren home, disabled dates | 4.75
2017-12-12 | validatie | 2
2017-12-15 | validatie | 1
2017-12-18 | validatie + image slider | 3.25
2017-12-19 | image toevoegen | 3
2017-12-22 | image toevoegen | 4.25
2017-12-23 | delete vehicle, add extra fields, proberen rollen, image add | 3.75
2017-12-24 | add review, uninstall + install module,opnieuw velden, rest, data,.. Toevoegen | 3
2017-12-26 | opnieuw velden, rest, data,.. Toevoegen | 4.5
2017-12-27 | prijs berekenen, beschikbare dagen, reviews | 4
2017-12-28 | Review, login nodig, booking, disabled days home, css | 4.5
2018-01-02 | Dossier afwerken + dossier development, deliver, deploy | 3.75
2018-01-02 | Afwerken: laadpunten eigenaar toevoegen, disabled days aanpassen, add voertuig problemen, status aanpassen boekingen, link naar detail bij bookings en request, css + validatie | 4
2018-01-03 | Vuex, add/edit vehicle + validate | 4.5
2018-01-04 | Add vehicle with unavailabled days en opties, edit opties + add/edit vehicle fixen | 3.75
2018-01-05 | edit opties + add/edit vehicle fixen | 2.75
2018-01-05 | Booking status, disabled days home + problems, profile edit | 4
2018-01-06 | Request countries, profile, css | 3
2018-01-18 | Deadline
| Totaal: | 225.25